## Sheet1
Reflection Log of Trust Indictor
| Project Phase | Key Events/Issues | Successes | challenges | Key Learning | Reflections and Lessons Learned | Follow-Up Actions | Status
Reflection 1 (Time: Week 2) | Project General Planning | Examined project handover reports, design documents, and technical guides. These documents were critical in gaining a foundational understanding of the project’s goals, architecture, and past work. Set up the development environment, ran the application locally, and studied key components. This exploration helped in understanding how the various modules interact and where to focus future development efforts. Held meetings to share insights and plan next steps. These discussions ensured that all team members were on the same page and could contribute their observations and ideas. | The detailed documentation provided by the previous team was invaluable. It served as a guide for understanding the project’s objectives, design, and implementation details, significantly reducing the learning curve. Successfully set up the development environment and ran the application locally, which is a crucial step for active development and testing. Our team was able to align on next steps through effective discussions, setting the stage for organized and focused efforts moving forward. | Encountered initial setup issues, such as dependency conflicts and environment mismatches. These were resolved through collaboration, sharing knowledge among team members, and documenting solutions for future reference. The project’s complexity, including multiple interconnected components and intricate business logic, required a significant time investment to fully understand. While this was a challenge, it was necessary for effective future development. | Documentation Value: Detailed and well-maintained documentation is crucial for onboarding new team members and ensuring they understand the project quickly. It provides a roadmap for navigating complex projects. Code Structure: Gained familiarity with the project’s code organization and functionality, which is essential for efficiently navigating the codebase and making informed decisions about where and how to implement changes or new features. | The initial setup and codebase exploration phase underscored the importance of having a standardized and well-documented setup process to reduce onboarding time and effort. Future teams will benefit from a clear guide. Collaborative problem-solving was effective. Encouraging team members to share their setup challenges and solutions can lead to faster resolutions and a more cohesive team environment. Understanding both the high-level architecture and low-level implementation details of the project is vital. A balanced approach ensures that developers are both informed and effective in their roles. | Continue Detailed Code Review: Spend more time reviewing specific components of the codebase to gain deeper insights into its functionality and dependencies. Assign Specific Tasks: Based on the initial understanding, assign tasks to team members that align with their expertise and interests. This will ensure that each member can contribute effectively and gain ownership of certain project areas. Schedule Regular Checks: Set up regular checks to monitor progress, address any new challenges that arise, and ensure continuous alignment among team members. | Finished
Reflection 2 (Time: Week 4) | Project Preparing and Team Operation Management | Gained more detailed information about project requirements through further contact with the client, laying a foundation for subsequent project advancement. Improvements in internal team management, with adjustments to the organizational structure to ensure each subgroup has a designated leader and setting regular meeting times. While compiling audit feedback, several key issues needing immediate adjustment were identified, providing direction for the next project phase. | Successfully completed the first phase audit1, with the team performing well during the audit, receiving recognition from both the client and the audit team. Internal team familiarity was enhanced through team-building activities and interactions, fostering a more collaborative work environment. | Communication and coordination within the team remain insufficient; some tasks lack clear allocation, leading to reduced work efficiency. Some members do not fully understand the overall project goals and their responsibilities, necessitating better guidance and support. | Learned the importance of KPIs in tutorials, which help clarify each team member’s objectives and responsibilities. KPIs can aid in better monitoring project progress and provide a basis for team improvement. | Reflection revealed that current task allocation and organizational structure are not clear enough; roles and responsibilities need to be more defined. KPIs and other metrics should be introduced to track and improve team efficiency, ensuring alignment of team goals | Hold a meeting immediately to redefine each team member’s responsibilities and tasks to ensure everyone understands their role. Establish KPIs to monitor the performance of each team member and regularly assess team progress. Develop a regular communication and feedback process, such as weekly team meetings and regular one-on-one feedback sessions, to improve team communication efficiency. | Finished
Reflection 3 (Time: Week 5) | Keep Team Operating Management | Developed a detailed task implementation plan, clarifying the project’s main tasks and objectives, providing direction for the smooth implementation of the project. With task allocation clarified, each team member understands their responsibilities and work content, contributing to improved work efficiency. | Through a series of meetings and discussions, the project process was further clarified and advanced, with team members gaining a deeper understanding of the project goals. Potential risks and issues were successfully identified during the meetings, and preliminary response strategies were developed. | Communication within the team still suffers from inefficiency; some crucial information was not shared in a timely manner, resulting in inadequate task preparation, such as for the elevator pitch presentation. There are issues with updating and maintaining task documentation, leading to inconsistent information and different interpretations of tasks among team members. | Learned the importance of keeping task documentation updated and consistent through collaboration and learning from the shadow team. Gained insights into how to better organize and present task information, ensuring team members can access the latest information. | The team needs to enhance communication to ensure all members receive relevant information timely, preventing misunderstandings and errors due to information asymmetry. Clear and updated task documentation is critical to ensuring consistent information and smooth task execution during the project implementation phase; a documentation update process and responsible person need to be established. | Immediately hold a communication meeting to discuss how to improve internal communication efficiency and develop effective communication strategies. Establish a document management process to ensure all documents are updated promptly and assign specific personnel responsible for document maintenance and management. Further communicate with the client to complete the initial project design, ensuring the design plan is understood and agreed upon by the team before audit2. | Working